## W1
PROJECT REPORT
Group | Group 1
Week | 10/05/2022-14/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Database | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Table Customes and Employees, Qlusers | Đỗ Hoàng Sơn
2 | Table Room and RoomType | Trịnh Công Hậu
3 | Table Service and ServiceType | Đoàn Quang Nhật Minh
4 | Table Bill and Voucher | Trần Quang Huy
5 | Table BookRoom and UseService | Nguyễn Trọng Hiếu
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Write Report Design | 22/05/2022
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W2
PROJECT REPORT
Group | Group 1
Week | 16/05/2022-22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Write Report Design | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Detailed Design | Đỗ Hoàng Sơn
2 | Sequence Diagram | Trịnh Công Hậu
3 | Sequence Diagram | Đoàn Quang Nhật Minh
4 | Database Design | Trần Quang Huy
5 | Sequence Diagram | Nguyễn Trọng Hiếu
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Write Report SRS | 29/05/2022
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W3
PROJECT REPORT
Group | Group 1
Week | 23/05/2022-29/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Write Report SRS | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Non-Functional Requirements | Đỗ Hoàng Sơn
2 | Functional Requirements | Trịnh Công Hậu
3 | User Requirements | Đoàn Quang Nhật Minh
4 | Introduction | Trần Quang Huy
5 | Overall Description | Nguyễn Trọng Hiếu
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Create Database in SQL | 2022-05-06
2 | Create Web Hotel | 2022-10-07
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W4-W9
PROJECT REPORT
Group | Group 1
Week | 30/05/2022-10/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Create Database in SQL | Completed
2 | Create web hotel | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Login, Sign up, Logout | Đỗ Hoàng Sơn
2 | Admin | Trịnh Công Hậu, Nguyễn Trọng Hiếu
3 | Frontend and Backend | Đoàn Quang Nhật Minh, Trần Quang Huy
4 | Database | All menbers
5
6
7
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Login, Sign up, Logout, decentralization | Completed
2 | Admin | Completed
3 | Frontend and Backend | Completed
4 | Connect with database | Completed
5 | Database | Completed
6 | Booking | In Progress
7 | Use voucher | In Progress
8 | Set day check-in and check-out | In Progress
9 | Add service | In Progress
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W10
PROJECT REPORT
Group | Group 1
Week | 11/07/2022-17/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Presentation | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Login, Sign up, Logout | Đỗ Hoàng Sơn
2 | sequence diagram | Trịnh Công Hậu
3 | Use-case presentation | Đoàn Quang Nhật Minh
4 | Database ,development direction of the project | Trần Quang Huy
5 | presentation homepage interface | Nguyễn Trọng Hiếu
6
7
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue